|  |  |  |  |
| --- | --- | --- | --- |
| Project Name | Wargaming for AI (Group F) | | |
| Project Sponsor | Dr. John Reisner | Customer | Mr. Michael Seal |
| Project Manager | Abdulrahman Albaiz | Group | F |
| Project Start date | Jan 17, 2022 | Project End date | Mar 21, 2022 |

| 1. Project Plan / Milestones (Shape     Description automatically generated with low confidence) |
| --- |
| |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | | **#** | **Task Name** | **Assigned To**  **Prime / Backup** | **Start** | **Finish** | **Status** | | **+** | **Requirements Phase** | **-** | **Jan 17** | **Jan 30** |  | | **1** | Refine Requirements | RL / CK | Jan 17 | Jan 30 |  | | **2** | Develop Prototype | CK / RL | Jan 17 | Jan 30 |  | | **3** | Sign-off Requirements Document Shape  Description automatically generated with low confidence | MS with RL | Jan 30 | Jan 30 |  | | **+** | **Analysis and Design Phase** | **-** | **Jan 31** | **Feb 6** |  | | **4** | Agree on the technology (language, database..) | CK / AS | Jan 31 | Feb 1 |  | | **5** | Develop Solution Design | CK / AS | Jan 31 | Feb 6 |  | | **6** | Develop Use Cases | AS / CK | Jan 31 | Feb 6 |  | | **7** | Develop Design Document Shape  Description automatically generated with low confidence | AS / CK | Jan 31 | Feb 6 |  | | **+** | **Implementation Phase** | **-** | **Feb 7** | **Feb 27** |  | | **8** | Develop the solution | CK / AS | Feb 7 | Feb 27 |  | | **9** | Unit/module testing | CK / AS | Feb 7 | Feb 27 |  | | **10** | Completion of the implementation phaseShape  Description automatically generated with low confidence |  | Feb 27 | Feb 27 |  | | **+** | **Testing Phase** | **-** | **Feb 21** | **Mar 13** |  | | **10** | Develop Test Plan and UAT Form | DC / RL | Feb 21 | Feb 27 |  | |  | *-------------- Spring Break --------------* |  | *Feb 28* | *Mar 6* |  | | **11** | Conduct Testing & Quality Assurance | DC / RL / AA | Mar 7 | Mar 8 |  | | **12** | Update Solution Based on Test Results | CK / AS | Mar 9 | Mar 13 |  | | **13** | User Acceptance Testing (UAT) Shape  Description automatically generated with low confidence | MS with CK | Mar 14 | Mar 14 |  | | **14** | Develop User’s Guide | DC | Mar 14 | Mar 15 |  | | **15** | End-User Training | DC | Mar 16 | Mar 16 |  | | **16** | Provide End-User Support | DC | Mar 16 | Mar 18 |  | | **17** | Develop Documentations | ALL / AA | Jan 17 | Mar 20 |  | | **18** | Create Project Presentation | AA | Mar 14 | Mar 21 |  | | **19** | Conduct Project Presentation Shape  Description automatically generated with low confidence | TBD | Mar 21 | Mar 21 |  | | **20** | Project Handover and Closing | ALL | Mar 22 | Mar 25 |  | |  | **Project Completed** Shape  Description automatically generated with low confidence | - | **Mar 25** | **Mar 25** |  |  * The backup person will be assisting the prime assignee with key tasks and will be shadowing him to take the lead in case the prime could not complete the task for any reason. This is part of the Project Risk Management Plan. |

| 1. Project Team | | | |
| --- | --- | --- | --- |
| Title | Name | Initials | Remarks |
| **Project Sponsor** | Dr. John Reisner | **JR** |  |
| **Customer** | Mr. Michael Seal | **MS** | Main User |
| **Project Manager** | Abdulrahman Albaiz | **AA** |  |
| **Lead Analyst** | Robert Linger | **RL** |  |
| **Lead Developer** | Christopher Kemplin | **CK** |  |
| **Comms Manager** | Ahmed Alsaedi | **AS** |  |
| **Lead Tester** | Daniel Curto | **DC** |  |